## Sheet1
Tasks and Assignment Breakdown
| Group: | The Nerd Herd
| Team Members (and initials): | Logan Levitre (LL), Jarett Nishijo (JN), Zeke Petersen (ZP), Jack Sanders (JS), Callista West (CW)
| Date this was last updated: | 2021-01-24
| Last updated by (whom): | ZP
In general, you should archive a copy of this spreadsheet (with the date in the file name) before modifying it.
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Phase 1
| Create v1 of SRS | not yet completed | ZP | 2021-01-19 |  | 2021-01-28 |  |  | 3
| Create v1 of SDS | not yet completed | ZP | 2021-01-19 |  | 2021-01-28 |  |  | 1
| Complete preprocessing module | not yet completed | LL | 2021-01-13 |  | 2021-01-28
| Complete modeling module | not yet completed | JN | 2021-01-13 |  | 2021-01-28
| Complete visualization module | not yet completed | JS | 2021-01-13 |  | 2021-01-28
| Establish tree data type and general n-ary operations | not yet completed | CW | 2021-01-19 |  | 2021-01-28
Phase 2
| Write functions for Loading/Saving Tree |  |  | 2021-01-28 |  | 2021-01-04
| Write functions for inserting nodes or subtrees, altering operators |  |  | 2021-01-28 |  | 2021-01-04
| Write functions for executing a tree, pipeline |  |  | 2021-01-28 |  | 2021-01-04
| Write functions for replicating a tree, pipeline |  |  | 2021-01-28 |  | 2021-01-04
| Create v2 of SDS |  |  | 2021-01-28 |  | 2021-01-04
| Create v2 of SRS |  |  | 2021-01-28 |  | 2021-01-04
Project Planning | [11 empty] | More planning notes in Logistics folder of repo
| Establish weekly meeting schedule. | completed | all staff | 2021-01-19 | N/A | N/A | 2021-01-19 | all staff | N/A | all staff | 2021-01-19 | Team meetings on Thursdays at 6PM, extra meetings scheduled by smaller groups as needed
| Establish shared repository | completed | JN | N/A | N/A | 2021-01-28 |  | JN |  | ZP | 2021-01-13
| Create standards document for code consistency, meeting writeup doc, README, planning spreadsheet | completed | ZP | 2021-01-13 | 2 | 2021-01-28 | 2021-01-15 | ZP | 1.5 |  |  | Living documents, will change as time goes on
| Initial team meeting | completed | all staff | 2021-01-13 | 30 mins | 2021-01-13 | 2021-01-13 | all staff | 20 mins | all staff | 2021-01-13
| Impromptu meeting | completed | all staff | 2021-01-19 | 30 mins | 2021-01-19 | 2021-01-19 | all staff | 20 mins | all staff | 2021-01-19
| First meeting with client | completed | all staff | 2021-01-20 | 30 mins | 2021-01-20 | 2021-01-20 | all staff | 15 mins | all staff | 2021-01-20
| Mandatory meeting 1 | completed | all staff | 2021-01-21 | 20 mins | 2021-01-21 | 2021-01-21 | ZP, LL, CW | 20 mins | all staff | 2021-01-21
| Week 3 Group Meeting | completed | all staff | 2021-01-21 | 20 mins | 2021-01-21 | 2021-01-21 | all staff | 30 mins | all staff | 2021-01-21
| Week 4 Group Meeting | not yet completed | all staff | 2021-01-28 | 30 mins | 2021-01-28
| Mandatory meeting 2 | not yet completed | all staff | 2021-01-04 | 20 mins | 2021-01-04